## Issues
Issue Key | Summary | Issue Type | Status | Priority | Assignee | Story Points | Sprint | Created Date | Due Date | Labels | Components | Dependencies
DPLAT-301 | Migrate data warehouse to Snowflake | Epic | In Progress | Critical | Maria Garcia | 40 | Sprint 3-6 | 2024-01-02 | 2024-02-28 | migration,snowflake | Data Warehouse | None
DPLAT-302 | ETL pipeline redesign | Story | In Progress | Critical | Chen Wei | 21 | Sprint 5 | 2024-01-10 | 2024-02-08 | etl,pipeline | ETL | DPLAT-301
DPLAT-303 | Real-time streaming implementation | Story | Blocked | Critical | Maria Garcia | 21 | Sprint 5 | 2024-01-12 | 2024-02-10 | streaming,kafka,blocked | Streaming | DPLAT-302
DPLAT-304 | Data quality framework setup | Story | In Progress | High | Robert Kim | 13 | Sprint 5 | 2024-01-15 | 2024-02-12 | quality,governance | Quality | DPLAT-301
DPLAT-305 | Legacy report migration | Story | To Do | Medium | Chen Wei | 8 | Sprint 6 | 2024-01-20 | 2024-02-20 | reports,legacy | Reports | DPLAT-302,DPLAT-304
DPLAT-306 | Data catalog implementation | Story | Blocked | High | Robert Kim | 13 | Sprint 5 | 2024-01-18 | 2024-02-15 | catalog,blocked | Catalog | DPLAT-304
DPLAT-307 | Access control and governance | Task | In Progress | Critical | Maria Garcia | 8 | Sprint 5 | 2024-01-14 | 2024-02-10 | security,governance | Security | DPLAT-301
DPLAT-308 | Performance benchmarking | Task | Done | High | Chen Wei | 5 | Sprint 4 | 2024-01-08 | 2024-01-25 | performance | Performance | DPLAT-301
DPLAT-309 | Disaster recovery setup | Task | To Do | Critical | Robert Kim | 8 | Sprint 6 | 2024-01-22 | 2024-02-22 | dr,infrastructure | Infrastructure | DPLAT-301
DPLAT-310 | API layer for data access | Story | In Progress | High | Maria Garcia | 13 | Sprint 5 | 2024-01-16 | 2024-02-14 | api,access | API | DPLAT-302
DPLAT-311 | Machine learning feature store | Story | To Do | Medium | Chen Wei | 13 | Sprint 6 | 2024-01-25 | 2024-02-25 | ml,features | ML | DPLAT-302,DPLAT-304
DPLAT-312 | Cost optimization analysis | Task | Done | Medium | Robert Kim | 5 | Sprint 4 | 2024-01-06 | 2024-01-20 | cost,finops | FinOps | None
DPLAT-313 | Documentation and training | Task | In Progress | High | Maria Garcia | 8 | Sprint 5 | 2024-01-19 | 2024-02-18 | documentation | Documentation | All
DPLAT-314 | Stakeholder UAT coordination | Task | To Do | High | PM - Nancy Drew | 5 | Sprint 6 | 2024-01-28 | 2024-02-24 | uat,stakeholders | UAT | DPLAT-305
DPLAT-315 | Production cutover planning | Task | To Do | Critical | PM - Nancy Drew | 8 | Sprint 6 | 2024-01-30 | 2024-02-28 | cutover,critical | Operations | All

## Sprints
Sprint Name | Start Date | End Date | Status | Committed Points | Completed Points | Sprint Goal
Sprint 3 | 2024-01-01 | 2024-01-14 | Completed | 45 | 38 | Snowflake setup
Sprint 4 | 2024-01-15 | 2024-01-28 | Completed | 50 | 42 | Initial migration
Sprint 5 | 2024-01-29 | 2024-02-11 | Active | 89 | 18 | ETL and streaming
Sprint 6 | 2024-02-12 | 2024-02-25 | Future | 55 | 0 | Cutover prep

## Risk Register
Risk ID | Description | Probability | Impact | Risk Score | Mitigation | Owner | Status | Identified Date
DPLAT-R1 | Snowflake costs exceeding budget projections by 40% | High | Critical | 9 | FinOps review, query optimization, reserved capacity | Robert Kim | Active | 2024-01-20
DPLAT-R2 | Kafka cluster stability issues in staging | High | Critical | 9 | Vendor support engaged, fallback to batch processing | Maria Garcia | Active | 2024-01-25
DPLAT-R3 | Key data engineer resignation - knowledge transfer incomplete | Occurred | Critical | 10 | Emergency contractor hire, documentation sprint | PM - Nancy Drew | Occurred | 2024-01-28
DPLAT-R4 | Legacy system dependencies not fully documented | High | High | 6 | Discovery sessions with legacy team | Chen Wei | Active | 2024-01-22
DPLAT-R5 | Compliance audit scheduled during cutover window | Medium | High | 6 | Request audit date change, prepare documentation early | PM - Nancy Drew | Monitoring | 2024-01-30

## Blockers
Blocker ID | Related Issue | Description | Blocked Since | Days Blocked | Escalated | Escalated To | Resolution ETA | Impact
DPLAT-B1 | DPLAT-303 | Kafka cluster in staging environment experiencing frequent crashes - vendor investigating | 2024-01-25 | 6 | Yes | CTO | 2024-02-05 | Blocking streaming implementation, 21 story points, critical path
DPLAT-B2 | DPLAT-306 | Data catalog tool license procurement delayed by legal review | 2024-01-27 | 4 | Yes | VP Procurement | 2024-02-03 | Blocking data catalog, 13 story points
DPLAT-B3 | DPLAT-302 | ETL pipeline blocked waiting for source system access credentials | 2024-01-30 | 1 | No |  | 2024-02-01 | Blocking ETL redesign, 21 story points, critical path

## EVM Metrics
Metric | Value | Unit | Health
BAC (Budget at Completion) | 800000 | $ | Baseline
PV (Planned Value) | 480000 | $ | On Track
EV (Earned Value) | 320000 | $ | Behind
AC (Actual Cost) | 420000 | $ | Over Budget
CV (Cost Variance) | -100000 | $ | Critical
SV (Schedule Variance) | -160000 | $ | Critical
CPI (Cost Performance Index) | 0.76 | ratio | Critical
SPI (Schedule Performance Index) | 0.67 | ratio | Critical
EAC (Estimate at Completion) | 1052632 | $ | Over Budget
ETC (Estimate to Complete) | 632632 | $ | N/A
VAC (Variance at Completion) | -252632 | $ | Critical
TCPI | 1.26 | ratio | Very Difficult
Percent Complete | 40 | % | N/A
Percent Spent | 52.5 | % | N/A

## Team
Name | Role | Allocation | Current Sprint Tasks | Velocity (Avg) | Notes
Maria Garcia | Data Architect | 100% | 4 | 12 | Overloaded
Chen Wei | Senior Data Engineer | 100% | 3 | 10 | Overloaded
Robert Kim | Data Engineer | 100% | 3 | 8 | Normal
Nancy Drew | Project Manager | 75% | 2 | 0 | Escalation focus
VACANT | Data Engineer (Resigned) | 0% | 0 | 8 | Left 2024-01-28