## Issues
Issue Key | Summary | Issue Type | Status | Priority | Assignee | Story Points | Sprint | Created Date | Due Date | Labels | Components
ECOM-101 | Migrate product catalog to new database | Story | Done | High | John Smith | 8 | Sprint 5 | 2024-01-15 | 2024-02-01 | migration,backend | Backend
ECOM-102 | Implement new checkout flow | Story | In Progress | Critical | Sarah Chen | 13 | Sprint 5 | 2024-01-20 | 2024-02-10 | frontend,critical-path | Frontend
ECOM-103 | Payment gateway integration | Story | In Progress | Critical | Mike Johnson | 13 | Sprint 5 | 2024-01-22 | 2024-02-15 | integration,payments | Payments
ECOM-104 | User authentication migration | Task | Done | High | John Smith | 5 | Sprint 4 | 2024-01-10 | 2024-01-25 | security,migration | Auth
ECOM-105 | Inventory sync with legacy system | Bug | Blocked | Critical | Sarah Chen | 8 | Sprint 5 | 2024-01-25 | 2024-02-08 | blocker,legacy | Inventory
ECOM-106 | Performance testing - load tests | Task | To Do | Medium | Alex Kumar | 5 | Sprint 6 | 2024-01-28 | 2024-02-20 | testing,performance | QA
ECOM-107 | Mobile responsive design updates | Story | In Review | Medium | Lisa Wang | 8 | Sprint 5 | 2024-01-18 | 2024-02-12 | frontend,mobile | Frontend
ECOM-108 | API rate limiting implementation | Task | Done | High | Mike Johnson | 3 | Sprint 4 | 2024-01-12 | 2024-01-28 | backend,security | Backend
ECOM-109 | Data migration scripts | Task | In Progress | High | John Smith | 8 | Sprint 5 | 2024-01-23 | 2024-02-10 | migration,data | Data
ECOM-110 | Rollback procedure documentation | Task | To Do | Low | Alex Kumar | 3 | Sprint 6 | 2024-01-30 | 2024-02-25 | documentation | DevOps

## Sprints
Sprint Name | Start Date | End Date | Status | Committed Points | Completed Points | Sprint Goal
Sprint 3 | 2024-01-01 | 2024-01-14 | Completed | 34 | 34 | Foundation setup
Sprint 4 | 2024-01-15 | 2024-01-28 | Completed | 42 | 38 | Auth and core APIs
Sprint 5 | 2024-01-29 | 2024-02-11 | Active | 55 | 29 | Payment and checkout
Sprint 6 | 2024-02-12 | 2024-02-25 | Future | 40 | 0 | Testing and polish

## Risk Register
Risk ID | Description | Probability | Impact | Risk Score | Mitigation | Owner | Status | Identified Date
ECOM-R1 | Payment gateway vendor may not meet SLA during peak | High | Critical | 9 | Negotiate backup vendor contract | Mike Johnson | Active | 2024-01-10
ECOM-R2 | Legacy system data quality issues discovered | Medium | High | 6 | Data cleansing sprint planned | John Smith | Mitigating | 2024-01-18
ECOM-R3 | Key developer on vacation during critical sprint | High | Medium | 6 | Cross-training team members | PM - Rachel Green | Active | 2024-01-25
ECOM-R4 | Third-party API deprecation announced | Low | High | 4 | Migration to new API version scheduled | Sarah Chen | Monitoring | 2024-01-28

## Blockers
Blocker ID | Related Issue | Description | Blocked Since | Days Blocked | Escalated | Escalated To | Resolution ETA | Impact
ECOM-B1 | ECOM-105 | Legacy inventory API returning inconsistent data formats | 2024-01-26 | 5 | Yes | VP Engineering | 2024-02-02 | Blocking 2 stories, 16 story points
ECOM-B2 | ECOM-103 | Payment gateway sandbox environment down for maintenance | 2024-01-30 | 1 | No |  | 2024-02-01 | Blocking 1 story, 13 story points

## EVM Metrics
Metric | Value | Unit | Health
BAC (Budget at Completion) | 500000 | $ | Baseline
PV (Planned Value) | 300000 | $ | On Track
EV (Earned Value) | 275000 | $ | Behind
AC (Actual Cost) | 290000 | $ | Over Budget
CV (Cost Variance) | -15000 | $ | At Risk
SV (Schedule Variance) | -25000 | $ | Behind
CPI (Cost Performance Index) | 0.95 | ratio | At Risk
SPI (Schedule Performance Index) | 0.92 | ratio | At Risk
EAC (Estimate at Completion) | 526316 | $ | Over Budget
ETC (Estimate to Complete) | 236316 | $ | N/A
VAC (Variance at Completion) | -26316 | $ | Over Budget
TCPI | 1.08 | ratio | Challenging
Percent Complete | 55 | % | N/A
Percent Spent | 58 | % | N/A

## Team
Name | Role | Allocation | Current Sprint Tasks | Velocity (Avg)
John Smith | Senior Backend Dev | 100% | 3 | 8
Sarah Chen | Full Stack Dev | 100% | 2 | 10
Mike Johnson | Payment Specialist | 75% | 2 | 6
Alex Kumar | QA Engineer | 50% | 1 | 4
Lisa Wang | Frontend Dev | 100% | 1 | 7
Rachel Green | Project Manager | 25% | 0 | 0