## Milestones
Milestone ID | Project | Milestone Name | Category | Planned Date | Forecast Date | Variance (Days) | Status | Percent Complete | Dependencies Met | Blocking Issues | Owner | Stakeholder Impact
M001 | ECOM | Architecture Sign-off | Technical | 2024-02-18 | 2024-02-18 | 0 | Completed | 100 | Yes | None | Rachel Green | Low
M002 | ECOM | Payment Gateway Live | Technical | 2024-03-15 | 2024-03-22 | 7 | At Risk | 45 | Partial | ECOM-B2 (Payment sandbox) | Mike Johnson | High
M003 | ECOM | UAT Complete | Quality | 2024-05-10 | 2024-05-17 | 7 | At Risk | 0 | No | Waiting on M002 | Rachel Green | High
M004 | ECOM | Go-Live | Delivery | 2024-05-24 | 2024-05-31 | 7 | At Risk | 0 | No | Waiting on M003 | Rachel Green | Critical
M005 | MOB | Beta Release | Delivery | 2024-02-01 | 2024-02-01 | 0 | Completed | 100 | Yes | None | Tom Harris | Medium
M006 | MOB | App Store Submission | Delivery | 2024-02-20 | 2024-02-22 | 2 | On Track | 80 | Yes | Apple review pending | Tom Harris | High
M007 | MOB | Public Launch | Delivery | 2024-03-01 | 2024-03-05 | 4 | On Track | 0 | No | Waiting on M006 | Tom Harris | Critical
M008 | DPLAT | Snowflake Migration Complete | Technical | 2024-02-15 | 2024-02-28 | 13 | Critical | 35 | Partial | DPLAT-B1 (Kafka) | Nancy Drew | High
M009 | DPLAT | ETL Pipeline Live | Technical | 2024-02-28 | 2024-03-15 | 15 | Critical | 20 | No | DPLAT-B3 (credentials) | Nancy Drew | High
M010 | DPLAT | Data Catalog Launch | Technical | 2024-03-10 | 2024-03-25 | 15 | Critical | 10 | No | DPLAT-B2 (license) | Nancy Drew | Medium
M011 | DPLAT | Full Cutover | Delivery | 2024-03-30 | 2024-04-20 | 21 | Critical | 0 | No | All upstream delayed | Nancy Drew | Critical
M012 | SOC2 | Policy Documentation Complete | Compliance | 2024-01-25 | 2024-01-25 | 0 | Completed | 100 | Yes | None | Compliance Lead | Medium
M013 | SOC2 | Technical Controls Implemented | Technical | 2024-02-10 | 2024-02-12 | 2 | On Track | 85 | Yes | Minor config pending | Security Team | High
M014 | SOC2 | Audit Readiness | Compliance | 2024-02-25 | 2024-02-20 | -5 | Ahead | 90 | Yes | None | Compliance Lead | High
M015 | SOC2 | SOC2 Certification | Compliance | 2024-03-15 | 2024-03-10 | -5 | Ahead | 60 | Partial | Vendor report pending | Compliance Lead | Critical

## Early Warning Alerts
Alert ID | Alert Type | Severity | Project | Related Milestone | Description | Days Until Deadline | Probability of Miss | Recommended Action | Created Date | Acknowledged
ALT001 | Deadline Risk | Critical | DPLAT | M008 | Snowflake migration 13 days behind schedule - critical path impact | 15 | 85% | Fast-track with additional resources, consider scope reduction | 2024-01-30 | Yes
ALT002 | Dependency Failure | Critical | ECOM | M002 | Payment gateway blocked by sandbox issue - 7 day delay projected | 44 | 60% | Escalate to payment vendor, prepare backup gateway | 2024-01-30 | Yes
ALT003 | Resource Constraint | High | DPLAT | M009 | Data team overloaded (124% utilization) - ETL pipeline at risk | 28 | 70% | Redistribute Maria Garcia workload, hire contractor | 2024-01-29 | No
ALT004 | Scope Creep | Medium | MOB | M007 | Feature requests added to Mobile v2.0 scope - 4 day impact | 30 | 40% | Scope review meeting, defer non-critical features to v2.1 | 2024-01-28 | Yes
ALT005 | Deadline Risk | Critical | DPLAT | M011 | Full cutover now projected 21 days late - executive escalation needed | 59 | 90% | Executive steering committee review, reset expectations | 2024-01-30 | No
ALT006 | Blocker Escalation | Critical | DPLAT | M008 | Kafka blocker unresolved for 6 days - vendor SLA breach | 15 | 80% | CTO escalation, invoke vendor penalty clause | 2024-01-30 | Yes
ALT007 | Budget Overrun | High | DPLAT | M011 | DPLAT projected to exceed budget by $252K (31% overrun) | 59 | 95% | FinOps review, request budget increase or scope reduction | 2024-01-30 | No
ALT008 | Quality Risk | Medium | ECOM | M003 | UAT preparation blocked by upstream delays | 100 | 55% | Parallel UAT prep where possible, daily standups | 2024-01-30 | No

## Milestone Trends
Snapshot Date | Milestone ID | Milestone Name | Forecast Date | Variance from Plan | Trend | Confidence Level
2024-01-08 | M002 | Payment Gateway Live | 2024-03-15 | 0 | Stable | 95%
2024-01-15 | M002 | Payment Gateway Live | 2024-03-15 | 0 | Stable | 90%
2024-01-22 | M002 | Payment Gateway Live | 2024-03-18 | 3 | Slipping | 75%
2024-01-29 | M002 | Payment Gateway Live | 2024-03-22 | 7 | Slipping | 60%
2024-01-08 | M008 | Snowflake Migration | 2024-02-15 | 0 | Stable | 90%
2024-01-15 | M008 | Snowflake Migration | 2024-02-18 | 3 | Slipping | 80%
2024-01-22 | M008 | Snowflake Migration | 2024-02-25 | 10 | Slipping | 50%
2024-01-29 | M008 | Snowflake Migration | 2024-02-28 | 13 | Critical | 35%
2024-01-08 | M011 | Full Cutover | 2024-03-30 | 0 | Stable | 85%
2024-01-15 | M011 | Full Cutover | 2024-04-05 | 6 | Slipping | 70%
2024-01-22 | M011 | Full Cutover | 2024-04-15 | 16 | Slipping | 45%
2024-01-29 | M011 | Full Cutover | 2024-04-20 | 21 | Critical | 25%

## Deadline Risk Matrix
Milestone | Days to Deadline | Current Progress % | Required Daily Progress % | Actual Daily Progress % | Progress Gap | Risk Level | Intervention Needed
M002 | 44 | 45 | 1.25 | 1 | -0.25 | Medium | Monitor
M003 | 100 | 0 | 1 | 0 | N/A | Low | Not yet
M004 | 114 | 0 | 0.88 | 0 | N/A | Low | Not yet
M008 | 15 | 35 | 4.33 | 1.5 | -2.83 | Critical | Immediate
M009 | 28 | 20 | 2.86 | 0.8 | -2.06 | High | This week
M010 | 39 | 10 | 2.31 | 0.4 | -1.91 | High | This week
M011 | 59 | 0 | 1.69 | 0 | -1.69 | Critical | Immediate
M015 | 44 | 60 | 0.91 | 1.5 | +0.59 | Low | No