## Issues
Issue Key | Summary | Issue Type | Status | Priority | Assignee | Story Points | Sprint | Created Date | Due Date | Labels | Components | Platform
MOB-201 | Implement biometric authentication | Story | Done | Critical | David Park | 8 | Sprint 4 | 2024-01-08 | 2024-01-28 | security,ios,android | Auth | iOS/Android
MOB-202 | Push notification service integration | Story | Done | High | Emma Wilson | 5 | Sprint 4 | 2024-01-10 | 2024-01-28 | backend,notifications | Backend | iOS/Android
MOB-203 | Offline mode data sync | Story | In Progress | High | David Park | 13 | Sprint 5 | 2024-01-15 | 2024-02-11 | offline,sync | Data | iOS/Android
MOB-204 | App performance optimization | Task | Done | Critical | James Lee | 5 | Sprint 4 | 2024-01-05 | 2024-01-25 | performance | Performance | iOS/Android
MOB-205 | Dark mode UI implementation | Story | In Progress | Medium | Sophie Brown | 8 | Sprint 5 | 2024-01-18 | 2024-02-08 | ui,design | UI | iOS/Android
MOB-206 | Crash reporting integration | Task | Done | High | James Lee | 3 | Sprint 4 | 2024-01-12 | 2024-01-26 | monitoring | DevOps | iOS/Android
MOB-207 | Deep linking support | Story | To Do | Medium | Emma Wilson | 5 | Sprint 6 | 2024-01-22 | 2024-02-20 | navigation | Navigation | iOS/Android
MOB-208 | In-app purchase flow | Story | In Progress | Critical | David Park | 13 | Sprint 5 | 2024-01-20 | 2024-02-15 | payments,revenue | Payments | iOS/Android
MOB-209 | User onboarding redesign | Story | Done | High | Sophie Brown | 8 | Sprint 4 | 2024-01-09 | 2024-01-30 | ux,onboarding | UX | iOS/Android
MOB-210 | Accessibility compliance (WCAG) | Task | In Review | High | Emma Wilson | 8 | Sprint 5 | 2024-01-25 | 2024-02-10 | accessibility,compliance | UI | iOS/Android
MOB-211 | Analytics SDK upgrade | Task | Done | Medium | James Lee | 3 | Sprint 4 | 2024-01-11 | 2024-01-27 | analytics | Analytics | iOS/Android
MOB-212 | App store optimization assets | Task | To Do | Low | Sophie Brown | 2 | Sprint 6 | 2024-01-28 | 2024-02-22 | marketing | Marketing | iOS/Android

## Sprints
Sprint Name | Start Date | End Date | Status | Committed Points | Completed Points | Sprint Goal
Sprint 3 | 2024-01-01 | 2024-01-14 | Completed | 40 | 40 | Core features
Sprint 4 | 2024-01-15 | 2024-01-28 | Completed | 45 | 45 | Auth and notifications
Sprint 5 | 2024-01-29 | 2024-02-11 | Active | 50 | 32 | Offline and payments
Sprint 6 | 2024-02-12 | 2024-02-25 | Future | 35 | 0 | Polish and launch prep

## Risk Register
Risk ID | Description | Probability | Impact | Risk Score | Mitigation | Owner | Status | Identified Date
MOB-R1 | Apple App Store review may delay launch | Medium | High | 6 | Submit early for pre-review, prepare expedited review request | PM - Tom Harris | Monitoring | 2024-01-15
MOB-R2 | Third-party SDK compatibility issues with iOS 17 | High | Medium | 6 | Testing on beta iOS versions, vendor communication | James Lee | Active | 2024-01-20
MOB-R3 | Performance regression on older Android devices | Medium | Medium | 4 | Device lab testing, performance budgets | David Park | Mitigating | 2024-01-22

## Blockers
Blocker ID | Related Issue | Description | Blocked Since | Days Blocked | Escalated | Escalated To | Resolution ETA | Impact
MOB-B1 | MOB-208 | Apple Pay sandbox certificate expired, waiting for renewal | 2024-01-29 | 2 | Yes | Finance Team | 2024-02-01 | Blocking in-app purchase testing, 13 story points

## EVM Metrics
Metric | Value | Unit | Health
BAC (Budget at Completion) | 350000 | $ | Baseline
PV (Planned Value) | 210000 | $ | On Track
EV (Earned Value) | 220000 | $ | Ahead
AC (Actual Cost) | 200000 | $ | Under Budget
CV (Cost Variance) | 20000 | $ | Favorable
SV (Schedule Variance) | 10000 | $ | Ahead
CPI (Cost Performance Index) | 1.1 | ratio | Healthy
SPI (Schedule Performance Index) | 1.05 | ratio | Healthy
EAC (Estimate at Completion) | 318182 | $ | Under Budget
ETC (Estimate to Complete) | 118182 | $ | N/A
VAC (Variance at Completion) | 31818 | $ | Favorable
TCPI | 0.93 | ratio | Achievable
Percent Complete | 63 | % | N/A
Percent Spent | 57 | % | N/A

## Team
Name | Role | Allocation | Current Sprint Tasks | Velocity (Avg)
David Park | iOS Lead | 100% | 3 | 10
Emma Wilson | Android Lead | 100% | 2 | 9
James Lee | Backend Dev | 75% | 1 | 6
Sophie Brown | UI/UX Designer | 100% | 2 | 7
Tom Harris | Project Manager | 50% | 0 | 0