## Portfolio Summary
Project | Project Key | Status | Health Score | Budget | Spent | CPI | SPI | Completion | Active Blockers | High Risks | Target Date | PM
E-Commerce Platform Migration | ECOM | At Risk | 65 | $500,000 | $290,000 (58%) | 0.95 | 0.92 | 55% | 2 | 2 | 2024-02-28 | Rachel Green
Mobile App v2.0 | MOB | On Track | 85 | $350,000 | $200,000 (57%) | 1.1 | 1.05 | 63% | 1 | 1 | 2024-02-25 | Tom Harris
Data Platform Modernization | DPLAT | Critical | 35 | $800,000 | $420,000 (52.5%) | 0.76 | 0.67 | 40% | 3 | 4 | 2024-02-28 | Nancy Drew
SOC2 Compliance Initiative | SOC2 | On Track | 78 | $150,000 | $95,000 (63%) | 1.05 | 0.95 | 67% | 0 | 1 | 2024-02-20 | Compliance Lead

## All Blockers
Project | Blocker ID | Description | Days Blocked | Escalated | Impact | Resolution ETA
ECOM | ECOM-B1 | Legacy inventory API returning inconsistent data formats | 5 | Yes | 16 SP | 2024-02-02
ECOM | ECOM-B2 | Payment gateway sandbox environment down for maintenance | 1 | No | 13 SP | 2024-02-01
MOB | MOB-B1 | Apple Pay sandbox certificate expired | 2 | Yes | 13 SP | 2024-02-01
DPLAT | DPLAT-B1 | Kafka cluster in staging experiencing frequent crashes | 6 | Yes | 21 SP Critical Path | 2024-02-05
DPLAT | DPLAT-B2 | Data catalog tool license procurement delayed | 4 | Yes | 13 SP | 2024-02-03
DPLAT | DPLAT-B3 | ETL pipeline blocked waiting for source system credentials | 1 | No | 21 SP Critical Path | 2024-02-01

## All Risks
Project | Risk ID | Description | Probability | Impact | Risk Score | Status | Owner
ECOM | ECOM-R1 | Payment gateway vendor may not meet SLA | High | Critical | 9 | Active | Mike Johnson
ECOM | ECOM-R3 | Key developer on vacation during critical sprint | High | Medium | 6 | Active | PM
MOB | MOB-R1 | Apple App Store review may delay launch | Medium | High | 6 | Monitoring | PM
MOB | MOB-R2 | Third-party SDK compatibility issues with iOS 17 | High | Medium | 6 | Active | James Lee
DPLAT | DPLAT-R1 | Snowflake costs exceeding budget by 40% | High | Critical | 9 | Active | Robert Kim
DPLAT | DPLAT-R2 | Kafka cluster stability issues in staging | High | Critical | 9 | Active | Maria Garcia
DPLAT | DPLAT-R3 | Key data engineer resignation | Occurred | Critical | 10 | Occurred | PM
DPLAT | DPLAT-R4 | Legacy system dependencies not documented | High | High | 6 | Active | Chen Wei
SOC2 | SOC2-R1 | Audit date moved up by 2 weeks | Occurred | High | 8 | Occurred | PM

## Resource Allocation
Name | Primary Project | Role | Allocation | Current Load | Active Tasks | Avg Velocity
John Smith | ECOM | Senior Backend Dev | 100% | High | 3 | 8
Sarah Chen | ECOM | Full Stack Dev | 100% | High | 2 | 10
Mike Johnson | ECOM | Payment Specialist | 75% | Medium | 2 | 6
David Park | MOB | iOS Lead | 100% | High | 3 | 10
Emma Wilson | MOB | Android Lead | 100% | Medium | 2 | 9
Maria Garcia | DPLAT | Data Architect | 100% | Overloaded | 4 | 12
Chen Wei | DPLAT | Senior Data Engineer | 100% | Overloaded | 3 | 10
Robert Kim | DPLAT | Data Engineer | 100% | High | 3 | 8