## Monte Carlo Simulation
Project | Scenario | Completion Date | Days from Plan | Final Cost ($) | Cost Variance ($) | Probability | Confidence
ECOM | P10 (Optimistic) | 2024-05-15 | -9 | 485000 | -15000 | 10% | Low
ECOM | P25 | 2024-05-20 | -4 | 495000 | -5000 | 15% | Low-Med
ECOM | P50 (Most Likely) | 2024-05-28 | 4 | 510000 | 10000 | 25% | Medium
ECOM | P75 | 2024-06-05 | 12 | 530000 | 30000 | 25% | Med-High
ECOM | P90 (Pessimistic) | 2024-06-15 | 22 | 565000 | 65000 | 25% | High
MOB | P10 (Optimistic) | 2024-02-22 | -7 | 335000 | -15000 | 10% | Low
MOB | P25 | 2024-02-25 | -4 | 342000 | -8000 | 20% | Low-Med
MOB | P50 (Most Likely) | 2024-03-01 | 0 | 350000 | 0 | 30% | Medium
MOB | P75 | 2024-03-05 | 4 | 362000 | 12000 | 25% | Med-High
MOB | P90 (Pessimistic) | 2024-03-12 | 11 | 385000 | 35000 | 15% | High
DPLAT | P10 (Optimistic) | 2024-03-25 | -5 | 850000 | 50000 | 5% | Very Low
DPLAT | P25 | 2024-04-08 | 9 | 920000 | 120000 | 15% | Low
DPLAT | P50 (Most Likely) | 2024-04-22 | 23 | 1000000 | 200000 | 30% | Medium
DPLAT | P75 | 2024-05-10 | 41 | 1100000 | 300000 | 30% | Med-High
DPLAT | P90 (Pessimistic) | 2024-05-28 | 59 | 1250000 | 450000 | 20% | High

## Velocity Forecasting
Project | Sprint | Committed Points | Completed Points | Velocity | Velocity Trend | Forecast Velocity | Remaining Points | Sprints to Complete
ECOM | Sprint 1 | 30 | 28 | 28 | Baseline
ECOM | Sprint 2 | 35 | 32 | 32 | Improving
ECOM | Sprint 3 | 34 | 34 | 34 | Stable
ECOM | Sprint 4 | 42 | 38 | 38 | Improving
ECOM | Sprint 5 | 55 | 29 | 29 | Declining
ECOM | Sprint 6 (Forecast) | 45 |  |  | Forecast: 32 | 32 | 85 | 2.7
MOB | Sprint 1 | 35 | 35 | 35 | Baseline
MOB | Sprint 2 | 38 | 38 | 38 | Improving
MOB | Sprint 3 | 40 | 40 | 40 | Stable
MOB | Sprint 4 | 45 | 45 | 45 | Improving
MOB | Sprint 5 | 50 | 32 | 32 | Declining
MOB | Sprint 6 (Forecast) | 42 |  |  | Forecast: 38 | 38 | 45 | 1.2
DPLAT | Sprint 1 | 40 | 35 | 35 | Baseline
DPLAT | Sprint 2 | 45 | 38 | 38 | Improving
DPLAT | Sprint 3 | 45 | 38 | 38 | Stable
DPLAT | Sprint 4 | 50 | 42 | 42 | Improving
DPLAT | Sprint 5 | 89 | 18 | 18 | Critical Drop
DPLAT | Sprint 6 (Forecast) | 55 |  |  | Forecast: 28 | 28 | 180 | 6.4

## Budget Burn Analysis
Project | Week | Planned Spend ($) | Actual Spend ($) | Cumulative Planned ($) | Cumulative Actual ($) | Burn Rate (Weekly) | Projected Final Cost ($) | Budget Remaining ($) | Weeks of Runway | Exhaustion Risk
ECOM | Week 1 | 50000 | 52000 | 50000 | 52000 | 52000 | 520000 | 448000 | 8.6 | Low
ECOM | Week 2 | 55000 | 58000 | 105000 | 110000 | 58000 | 522000 | 390000 | 6.7 | Low
ECOM | Week 3 | 60000 | 62000 | 165000 | 172000 | 62000 | 516000 | 328000 | 5.3 | Medium
ECOM | Week 4 | 65000 | 68000 | 230000 | 240000 | 68000 | 510000 | 260000 | 3.8 | Medium
ECOM | Week 5 (Current) | 70000 | 50000 | 300000 | 290000 | 50000 | 505000 | 210000 | 4.2 | Medium
MOB | Week 1 | 35000 | 32000 | 35000 | 32000 | 32000 | 340000 | 318000 | 9.9 | Low
MOB | Week 2 | 40000 | 38000 | 75000 | 70000 | 38000 | 345000 | 280000 | 7.4 | Low
MOB | Week 3 | 42000 | 40000 | 117000 | 110000 | 40000 | 348000 | 240000 | 6 | Low
MOB | Week 4 | 45000 | 42000 | 162000 | 152000 | 42000 | 350000 | 198000 | 4.7 | Medium
MOB | Week 5 (Current) | 48000 | 48000 | 210000 | 200000 | 48000 | 350000 | 150000 | 3.1 | Medium
DPLAT | Week 1 | 80000 | 85000 | 80000 | 85000 | 85000 | 950000 | 715000 | 8.4 | Medium
DPLAT | Week 2 | 90000 | 95000 | 170000 | 180000 | 95000 | 1020000 | 620000 | 6.5 | High
DPLAT | Week 3 | 95000 | 105000 | 265000 | 285000 | 105000 | 1050000 | 515000 | 4.9 | High
DPLAT | Week 4 | 100000 | 115000 | 365000 | 400000 | 115000 | 1080000 | 400000 | 3.5 | Critical
DPLAT | Week 5 (Current) | 115000 | 20000 | 480000 | 420000 | 20000 | 1050000 | 380000 | 19 | High

## Bottleneck Predictions
Prediction ID | Resource Type | Project Impact | Bottleneck Period | Demand (Hours) | Capacity (Hours) | Gap (Hours) | Severity | Confidence | Mitigation Options | Estimated Cost to Mitigate
BP001 | Data Engineer | DPLAT | 2024-02-05 to 2024-02-28 | 320 | 200 | 120 | Critical | 92% | Hire contractor ($110/hr) or redistribute from MOB | $13,200
BP002 | Kafka Specialist | DPLAT | 2024-02-01 to 2024-03-15 | 200 | 0 | 200 | Critical | 95% | Urgent contractor hire - no internal capacity | $25,000
BP003 | QA Engineer | ECOM, MOB | 2024-02-15 to 2024-03-01 | 280 | 160 | 120 | High | 85% | Shift Alex Kumar to 100%, defer non-critical tests | $0 (reallocation)
BP004 | DevOps | ECOM, DPLAT | 2024-02-20 to 2024-03-10 | 240 | 160 | 80 | High | 88% | James Lee overtime + contractor support | $8,000
BP005 | Frontend Dev | ECOM | 2024-02-10 to 2024-02-25 | 180 | 120 | 60 | Medium | 78% | Lisa Wang overtime or contractor | $6,000
BP006 | Security Analyst | SOC2, ECOM | 2024-02-15 to 2024-02-28 | 120 | 80 | 40 | Medium | 82% | Engage external consultant for audit prep | $10,000