## Team Members
Employee ID | Name | Role | Department | Primary Skills | Secondary Skills | Skill Level | Hourly Rate ($) | Max Hours/Week | Current Allocation % | Available From | Location | Timezone
EMP001 | John Smith | Senior Backend Dev | Engineering | Java,Python,AWS | Kubernetes,Docker | Senior | 150 | 40 | 100 | Allocated | NYC | EST
EMP002 | Sarah Chen | Full Stack Dev | Engineering | React,Node.js,Python | AWS,Docker | Mid | 120 | 40 | 100 | Allocated | SF | PST
EMP003 | Mike Johnson | Payment Specialist | Engineering | Stripe,PayPal,PCI-DSS | Node.js,Security | Senior | 140 | 30 | 75 | 2024-02-15 | NYC | EST
EMP004 | David Park | iOS Lead | Mobile | Swift,iOS,Xcode | SwiftUI,CoreData | Senior | 145 | 40 | 100 | Allocated | SF | PST
EMP005 | Emma Wilson | Android Lead | Mobile | Kotlin,Android,Firebase | Jetpack Compose | Senior | 145 | 40 | 100 | Allocated | SF | PST
EMP006 | Maria Garcia | Data Architect | Data | Snowflake,SQL,Data Modeling | AWS,Python | Principal | 175 | 40 | 100 | Allocated | Austin | CST
EMP007 | Chen Wei | Senior Data Engineer | Data | Python,Spark,Kafka | AWS,Docker | Senior | 150 | 40 | 100 | Allocated | Austin | CST
EMP008 | Robert Kim | Data Engineer | Data | SQL,ETL,Airflow | Python,dbt | Mid | 110 | 40 | 100 | Allocated | Austin | CST
EMP009 | Lisa Wang | Frontend Dev | Engineering | React,TypeScript,CSS | Node.js,GraphQL | Mid | 115 | 40 | 100 | Allocated | NYC | EST
EMP010 | Alex Kumar | QA Engineer | QA | Selenium,Jest,Cypress | Python,API Testing | Mid | 100 | 40 | 50 | 2024-02-01 | Remote | IST
EMP011 | Sophie Brown | UI/UX Designer | Design | Figma,Adobe XD,CSS | HTML,Prototyping | Senior | 125 | 40 | 100 | Allocated | London | GMT
EMP012 | James Lee | DevOps Engineer | DevOps | Kubernetes,Terraform,CI/CD | AWS,Python | Senior | 140 | 40 | 75 | 2024-02-10 | SF | PST

## Current Assignments
Assignment ID | Employee ID | Employee Name | Project | Task | Allocation % | Start Date | End Date | Hours Planned | Hours Actual | Status
A001 | EMP001 | John Smith | ECOM | API Development | 60 | 2024-01-15 | 2024-02-28 | 120 | 85 | In Progress
A002 | EMP002 | Sarah Chen | ECOM | Checkout Flow | 80 | 2024-01-20 | 2024-02-10 | 80 | 65 | In Progress
A003 | EMP001 | John Smith | DPLAT | Data Migration Support | 40 | 2024-01-22 | 2024-02-15 | 60 | 45 | In Progress
A004 | EMP003 | Mike Johnson | ECOM | Payment Integration | 75 | 2024-01-22 | 2024-02-15 | 90 | 70 | In Progress
A005 | EMP004 | David Park | MOB | Biometric Auth | 100 | 2024-01-08 | 2024-01-28 | 80 | 80 | Completed
A006 | EMP005 | Emma Wilson | MOB | Push Notifications | 100 | 2024-01-10 | 2024-01-28 | 72 | 72 | Completed
A007 | EMP006 | Maria Garcia | DPLAT | Snowflake Migration | 70 | 2024-01-02 | 2024-02-28 | 140 | 95 | In Progress
A008 | EMP007 | Chen Wei | DPLAT | ETL Pipeline | 100 | 2024-01-10 | 2024-02-08 | 120 | 90 | In Progress
A009 | EMP008 | Robert Kim | DPLAT | Data Quality | 100 | 2024-01-15 | 2024-02-12 | 100 | 75 | In Progress
A010 | EMP009 | Lisa Wang | ECOM | Mobile Responsive | 100 | 2024-01-18 | 2024-02-12 | 100 | 60 | In Progress
A011 | EMP010 | Alex Kumar | ECOM | Testing | 50 | 2024-01-25 | 2024-02-20 | 50 | 25 | In Progress
A012 | EMP011 | Sophie Brown | MOB | Dark Mode UI | 100 | 2024-01-18 | 2024-02-08 | 80 | 55 | In Progress
A013 | EMP012 | James Lee | ECOM | CI/CD Pipeline | 50 | 2024-01-15 | 2024-02-28 | 60 | 40 | In Progress
A014 | EMP002 | Sarah Chen | MOB | Offline Sync | 20 | 2024-01-15 | 2024-02-11 | 40 | 15 | In Progress
A015 | EMP006 | Maria Garcia | SOC2 | Data Governance | 30 | 2024-01-14 | 2024-02-10 | 40 | 30 | In Progress

## Workload Analysis
Employee ID | Name | Week 1 Hours | Week 2 Hours | Week 3 Hours | Week 4 Hours | Avg Weekly Hours | Utilization % | Workload Status | Burnout Risk | Recommended Action
EMP001 | John Smith | 45 | 48 | 50 | 42 | 46.25 | 116 | Overloaded | High | Redistribute 15% workload
EMP002 | Sarah Chen | 42 | 44 | 40 | 38 | 41 | 103 | Slightly Over | Medium | Monitor closely
EMP003 | Mike Johnson | 30 | 30 | 28 | 30 | 29.5 | 98 | Optimal | Low | Can take more work
EMP004 | David Park | 40 | 40 | 38 | 40 | 39.5 | 99 | Optimal | Low | Stable
EMP005 | Emma Wilson | 40 | 40 | 38 | 40 | 39.5 | 99 | Optimal | Low | Stable
EMP006 | Maria Garcia | 48 | 50 | 52 | 48 | 49.5 | 124 | Overloaded | Critical | Immediate redistribution needed
EMP007 | Chen Wei | 45 | 48 | 50 | 46 | 47.25 | 118 | Overloaded | High | Redistribute 20% workload
EMP008 | Robert Kim | 42 | 44 | 45 | 42 | 43.25 | 108 | Slightly Over | Medium | Monitor closely
EMP009 | Lisa Wang | 40 | 42 | 40 | 38 | 40 | 100 | Optimal | Low | Stable
EMP010 | Alex Kumar | 20 | 22 | 25 | 20 | 21.75 | 54 | Underutilized | Low | Assign to DPLAT support
EMP011 | Sophie Brown | 40 | 42 | 40 | 38 | 40 | 100 | Optimal | Low | Stable
EMP012 | James Lee | 35 | 38 | 40 | 35 | 37 | 93 | Optimal | Low | Can support DPLAT

## Skill Gap Analysis
Project | Required Skill | Current Coverage | Gap Severity | Available Internal | Recommendation | Estimated Training Time | Cost Impact
ECOM | Kubernetes | Partial | Medium | James Lee (DevOps) | Cross-train Sarah Chen | 2 weeks | $3,000
ECOM | GraphQL | None | High | None | Hire contractor or train Lisa | 4 weeks | $8,000
DPLAT | Kafka Administration | Partial | Critical | Chen Wei (learning) | Urgent: Hire Kafka specialist | N/A - hire | $25,000/month contractor
DPLAT | Snowflake Optimization | Limited | High | Maria Garcia | Training for Robert Kim | 3 weeks | $5,000
MOB | Flutter | None | Low | None | Not needed for v2.0 | N/A | $0
SOC2 | ISO 27001 | None | Medium | None | Engage compliance consultant | N/A - external | $15,000

## AI Recommendations
Recommendation ID | Type | Description | Impact | Priority | Estimated Savings/Cost | Timeline | Confidence Score
REC001 | Reallocation | Move Alex Kumar from 50% ECOM to 100% DPLAT to support data quality testing | Reduces DPLAT risk, minimal ECOM impact | High | $0 (reallocation) | Immediate | 92%
REC002 | Hiring | Hire Kafka specialist contractor for DPLAT - critical path blocker | Unblocks streaming implementation | Critical | -$25,000/month | 1 week to onboard | 95%
REC003 | Training | Enroll Robert Kim in Snowflake optimization course | Improves query performance 30% | Medium | -$5,000 (investment) | 3 weeks | 85%
REC004 | Reallocation | Reduce Maria Garcia DPLAT allocation from 70% to 50%, add SOC2 support | Balances workload, supports compliance | High | $0 (reallocation) | Next sprint | 88%
REC005 | Workload Balance | Redistribute John Smith tasks: move DPLAT support to James Lee | Reduces burnout risk for senior dev | High | $0 (efficiency gain) | Immediate | 90%
REC006 | Skill Development | Cross-train Sarah Chen on GraphQL for ECOM API layer | Enables API modernization | Medium | -$8,000 (investment) | 4 weeks | 82%