## Issues
Issue Key | Summary | Issue Type | Status | Priority | Assignee | Story Points | Sprint | Created Date | Due Date | Labels | Control Area | Audit Ready
SOC2-401 | Access control policy documentation | Task | Done | Critical | Security Team | 5 | Sprint 4 | 2024-01-05 | 2024-01-25 | documentation,policy | CC6.1 | Yes
SOC2-402 | Implement MFA across all systems | Story | Done | Critical | IT Ops | 13 | Sprint 4 | 2024-01-08 | 2024-01-28 | security,mfa | CC6.1, CC6.6 | Yes
SOC2-403 | Security awareness training program | Task | In Progress | High | HR/Security | 8 | Sprint 5 | 2024-01-15 | 2024-02-10 | training,awareness | CC1.4 | No
SOC2-404 | Vendor risk assessment process | Task | Done | High | Procurement | 5 | Sprint 4 | 2024-01-10 | 2024-01-26 | vendor,risk | CC9.2 | Yes
SOC2-405 | Incident response procedure update | Task | In Progress | Critical | Security Team | 8 | Sprint 5 | 2024-01-18 | 2024-02-08 | incident,response | CC7.4, CC7.5 | No
SOC2-406 | Data encryption audit | Task | Done | High | Security Team | 5 | Sprint 4 | 2024-01-12 | 2024-01-27 | encryption,audit | CC6.7 | Yes
SOC2-407 | Penetration testing coordination | Task | Done | Critical | External Vendor | 8 | Sprint 4 | 2024-01-06 | 2024-01-30 | pentest,security | CC4.1 | Yes
SOC2-408 | Audit log retention implementation | Story | In Progress | High | DevOps | 13 | Sprint 5 | 2024-01-20 | 2024-02-12 | logging,retention | CC7.2 | No
SOC2-409 | Business continuity plan update | Task | To Do | Medium | BCP Team | 8 | Sprint 6 | 2024-01-25 | 2024-02-20 | bcp,continuity | A1.2 | No
SOC2-410 | Evidence collection automation | Story | In Progress | High | DevOps | 13 | Sprint 5 | 2024-01-22 | 2024-02-15 | automation,evidence | CC4.1 | No

## Sprints
Sprint Name | Start Date | End Date | Status | Committed Points | Completed Points | Sprint Goal
Sprint 3 | 2024-01-01 | 2024-01-14 | Completed | 30 | 30 | Policy foundation
Sprint 4 | 2024-01-15 | 2024-01-28 | Completed | 44 | 44 | Core controls
Sprint 5 | 2024-01-29 | 2024-02-11 | Active | 42 | 15 | Training and logging
Sprint 6 | 2024-02-12 | 2024-02-25 | Future | 25 | 0 | Final prep

## Risk Register
Risk ID | Description | Probability | Impact | Risk Score | Mitigation | Owner | Status | Identified Date
SOC2-R1 | Audit date moved up by 2 weeks | Occurred | High | 8 | Accelerated timeline, weekend work approved | PM - Compliance Lead | Occurred | 2024-01-28
SOC2-R2 | Third-party vendor SOC2 report delayed | Medium | Medium | 4 | Alternative evidence collection, vendor escalation | Procurement | Monitoring | 2024-01-25

## Blockers
Blocker ID | Related Issue | Description | Blocked Since | Days Blocked | Escalated | Escalated To | Resolution ETA | Impact

## EVM Metrics
Metric | Value | Unit | Health
BAC (Budget at Completion) | 150000 | $ | Baseline
PV (Planned Value) | 105000 | $ | On Track
EV (Earned Value) | 100000 | $ | Slightly Behind
AC (Actual Cost) | 95000 | $ | Under Budget
CV (Cost Variance) | 5000 | $ | Favorable
SV (Schedule Variance) | -5000 | $ | Slightly Behind
CPI (Cost Performance Index) | 1.05 | ratio | Healthy
SPI (Schedule Performance Index) | 0.95 | ratio | At Risk
EAC (Estimate at Completion) | 142857 | $ | Under Budget
ETC (Estimate to Complete) | 47857 | $ | N/A
VAC (Variance at Completion) | 7143 | $ | Favorable
TCPI | 0.96 | ratio | Achievable
Percent Complete | 67 | % | N/A
Percent Spent | 63 | % | N/A

## Team
Name | Role | Allocation | Current Sprint Tasks | Velocity (Avg)
Security Team | Security Controls | 50% | 2 | 8
IT Ops | Infrastructure | 25% | 0 | 5
DevOps | Automation | 25% | 2 | 6
HR/Security | Training | 10% | 1 | 3
Compliance Lead | Project Manager | 100% | 0 | 0