## Task Schedule
Task ID | Task Name | Project | Duration (Days) | Predecessors | Start Date | End Date | Slack (Days) | Is Critical Path | Status | Percent Complete | Assigned Team
T001 | Requirements Gathering | ECOM | 10 |  | 2024-01-15 | 2024-01-28 | 0 | Yes | Completed | 100 | BA Team
T002 | System Architecture Design | ECOM | 15 | T001 | 2024-01-29 | 2024-02-18 | 0 | Yes | Completed | 100 | Architecture
T003 | Database Schema Design | ECOM | 8 | T002 | 2024-02-19 | 2024-02-28 | 0 | Yes | Completed | 100 | Data Team
T004 | API Development | ECOM | 20 | T002,T003 | 2024-03-01 | 2024-03-28 | 0 | Yes | In Progress | 65 | Backend Team
T005 | Frontend Development | ECOM | 25 | T002 | 2024-02-19 | 2024-03-22 | 12 | No | In Progress | 40 | Frontend Team
T006 | Backend Services | ECOM | 18 | T003,T004 | 2024-03-11 | 2024-04-05 | 0 | Yes | Not Started | 0 | Backend Team
T007 | Integration Testing | ECOM | 12 | T004,T005,T006 | 2024-04-08 | 2024-04-23 | 0 | Yes | Not Started | 0 | QA Team
T008 | Security Audit | ECOM | 5 | T007 | 2024-04-24 | 2024-04-30 | 0 | Yes | Not Started | 0 | Security
T009 | Performance Testing | ECOM | 8 | T007 | 2024-04-24 | 2024-05-03 | 2 | No | Not Started | 0 | QA Team
T010 | UAT Preparation | ECOM | 5 | T008,T009 | 2024-05-03 | 2024-05-09 | 0 | Yes | Not Started | 0 | BA Team
T011 | User Training | ECOM | 3 | T010 | 2024-05-10 | 2024-05-14 | 5 | No | Not Started | 0 | Training
T012 | Documentation | ECOM | 10 | T007 | 2024-04-24 | 2024-05-07 | 8 | No | Not Started | 0 | Tech Writers
T013 | Deployment Planning | ECOM | 5 | T010,T012 | 2024-05-15 | 2024-05-21 | 0 | Yes | Not Started | 0 | DevOps
T014 | Go-Live Execution | ECOM | 2 | T013 | 2024-05-22 | 2024-05-23 | 0 | Yes | Not Started | 0 | DevOps
T015 | Post-Launch Support | ECOM | 14 | T014 | 2024-05-24 | 2024-06-10 | 0 | Yes | Not Started | 0 | Support

## Compression Opportunities
Opportunity ID | Task | Current Duration | Compressed Duration | Compression Method | Additional Cost | Risk Level | Days Saved | Recommendation | Impact on Critical Path
SC001 | API Development | 20 | 15 | Fast-tracking with parallel streams | $0 | Medium | 5 | Recommended | Yes - saves 5 days
SC002 | Frontend Development | 25 | 18 | Add 2 developers (crashing) | $15,000 | Low | 7 | Highly Recommended | No - has slack
SC003 | Integration Testing | 12 | 8 | Automated test suite | $5,000 | Low | 4 | Recommended | Yes - saves 4 days
SC004 | Documentation | 10 | 6 | Use AI documentation tools | $2,000 | Low | 4 | Recommended | No - has slack

## Dependency Matrix
Task | T001 | T002 | T003 | T004 | T005 | T006 | T007 | T008 | T009 | T010
T001 | -
T002 | FS | -
T003 |  | FS | -
T004 |  | FS | FS | -
T005 |  | FS |  |  | -
T006 |  |  | FS | FS |  | -
T007 |  |  |  | FS | FS | FS | -
T008 | [6 empty] | FS | -
T009 | [6 empty] | FS |  | -
T010 | [7 empty] | FS | FS | -