## Stakeholder Registry
Stakeholder ID | Name | Title | Organization | Influence Level | Interest Level | Communication Preference | Preferred Format | Frequency | Projects of Interest | Email | Last Communication
STK001 | Jennifer Walsh | CEO | Executive | Critical | Medium | Executive Summary | 1-page PDF | Monthly | All | jwelsh@company.com | 2024-01-15
STK002 | Michael Torres | CTO | Executive | Critical | High | Technical Detail | Dashboard + Detail | Weekly | All | mtorres@company.com | 2024-01-29
STK003 | Amanda Chen | CFO | Executive | Critical | High | Financial Focus | Spreadsheet | Weekly | All | achen@company.com | 2024-01-29
STK004 | Robert Stevens | VP Engineering | Engineering | High | High | Technical Detail | Dashboard | Weekly | ECOM, DPLAT | rstevens@company.com | 2024-01-28
STK005 | Lisa Park | VP Product | Product | High | High | Feature Focus | Slides | Bi-weekly | MOB, ECOM | lpark@company.com | 2024-01-22
STK006 | David Kim | Director PMO | PMO | High | Critical | Full Detail | Full Report | Daily | All | dkim@company.com | 2024-01-30
STK007 | Sarah Johnson | Director Data | Data | High | Critical | Data Focus | Dashboard | Weekly | DPLAT | sjohnson@company.com | 2024-01-29
STK008 | Chris Martinez | Head of Security | Security | Medium | Medium | Security Focus | Checklist | Bi-weekly | SOC2, ECOM | cmartinez@company.com | 2024-01-20
STK009 | Emily Brown | Head of Mobile | Mobile | Medium | High | Mobile Focus | Demo + Slides | Weekly | MOB | ebrown@company.com | 2024-01-28
STK010 | James Wilson | Head of E-Commerce | E-Commerce | Medium | High | E-Commerce Focus | Dashboard | Weekly | ECOM | jwilson@company.com | 2024-01-28

## Communication Calendar
Event ID | Event Type | Date | Time | Duration | Project | Attendees | Agenda Items | Materials Needed | Auto-Generate | Status
COM001 | SteerCo Meeting | 2024-02-01 | 10:00 AM | 60 min | All | Executives, PMs | Portfolio status, DPLAT escalation, Q1 forecast | Executive dashboard, risk summary | Yes | Scheduled
COM002 | Weekly Status | 2024-02-02 | 9:00 AM | 30 min | ECOM | ECOM Team, Stakeholders | Sprint 5 progress, blocker updates, next week plan | Sprint burndown, blocker list | Yes | Scheduled
COM003 | Budget Review | 2024-02-05 | 2:00 PM | 45 min | DPLAT | Finance, DPLAT PM | Budget overrun analysis, mitigation options | EVM report, forecast | Yes | Scheduled
COM004 | Sprint Review | 2024-02-02 | 3:00 PM | 60 min | MOB | MOB Team, Product | Sprint 5 demo, v2.0 readiness, launch plan | Demo environment, slides | No | Scheduled
COM005 | Risk Review | 2024-02-06 | 11:00 AM | 30 min | All | PMs, Risk Owners | Risk register review, new risks, mitigation status | Risk register, heat map | Yes | Scheduled
COM006 | SteerCo Meeting | 2024-02-15 | 10:00 AM | 60 min | All | Executives, PMs | Portfolio status, milestone updates, Q1 close | Executive dashboard | Yes | Scheduled
COM007 | Weekly Status | 2024-02-09 | 9:00 AM | 30 min | DPLAT | DPLAT Team, Stakeholders | Migration status, blocker resolution, timeline | Technical status, timeline | Yes | Scheduled
COM008 | Milestone Review | 2024-02-08 | 1:00 PM | 45 min | ECOM | ECOM PM, Stakeholders | Payment gateway milestone, UAT planning | Milestone tracker | Yes | Scheduled
COM009 | Executive Briefing | 2024-02-12 | 4:00 PM | 30 min | DPLAT | CEO, CTO, CFO | DPLAT recovery plan, budget request | Recovery plan doc | Yes | Pending Approval
COM010 | Sprint Planning | 2024-02-05 | 10:00 AM | 60 min | ECOM | ECOM Team | Sprint 6 planning, capacity, commitments | Backlog, capacity plan | No | Scheduled

## Sentiment Analysis
Feedback ID | Date | Stakeholder | Project | Channel | Feedback Summary | Sentiment | Sentiment Score | Key Concerns | Action Required | Follow-up Date
FB001 | 2024-01-29 | Michael Torres (CTO) | DPLAT | SteerCo Meeting | Concerned about Kafka issues and timeline slip | Negative | -0.6 | Timeline, Technical Risk | Recovery plan presentation | 2024-02-01
FB002 | 2024-01-28 | Amanda Chen (CFO) | DPLAT | Email | Budget overrun unacceptable, need recovery plan | Negative | -0.8 | Budget, ROI | Budget mitigation options | 2024-02-05
FB003 | 2024-01-25 | Lisa Park (VP Product) | MOB | Sprint Review | Happy with mobile progress, excited for launch | Positive | 0.7 | None | Continue current approach | N/A
FB004 | 2024-01-22 | Robert Stevens (VP Eng) | ECOM | Slack | Payment blocker frustrating, need vendor escalation | Negative | -0.5 | Vendor, Blocker | Vendor escalation update | 2024-01-31
FB005 | 2024-01-29 | Jennifer Walsh (CEO) | All | Executive Briefing | Need clear picture of Q1 delivery across portfolio | Neutral | 0 | Visibility, Predictability | Portfolio dashboard enhancement | 2024-02-01
FB006 | 2024-01-26 | David Kim (PMO Dir) | DPLAT | Status Meeting | DPLAT needs immediate intervention | Negative | -0.7 | Timeline, Resources | War room setup | 2024-01-31
FB007 | 2024-01-30 | Sarah Johnson (Dir Data) | DPLAT | Email | Worried about data quality with rushed timeline | Concerned | -0.4 | Quality, Technical Debt | Quality gates review | 2024-02-02
FB008 | 2024-01-28 | Emily Brown (Head Mobile) | MOB | Sprint Review | Team morale high, good velocity | Positive | 0.8 | None | Recognition for team | N/A

## Meeting Templates
Template ID | Template Name | Audience | Duration | Sections | Auto-Generated Content | Talking Points Auto-Gen | Last Used
TPL001 | SteerCo Briefing | Executives | 60 min | Executive Summary ¦ Portfolio Health ¦ Critical Issues ¦ Decisions Needed ¦ Next Steps | Health dashboard, risk summary, blocker list, EVM snapshot | Yes | 2024-01-15
TPL002 | Weekly Status | Team + Stakeholders | 30 min | Sprint Progress ¦ Blockers ¦ Risks ¦ Next Week ¦ Help Needed | Burndown chart, blocker status, risk updates | Yes | 2024-01-29
TPL003 | Budget Review | Finance + PM | 45 min | Budget Status ¦ EVM Metrics ¦ Variance Analysis ¦ Forecast ¦ Recommendations | EVM report, burn chart, forecast scenarios | Yes | 2024-01-22
TPL004 | Risk Review | PM + Risk Owners | 30 min | Risk Register ¦ New Risks ¦ Mitigation Status ¦ Escalations ¦ Action Items | Risk heat map, trend analysis, mitigation tracker | Yes | 2024-01-23
TPL005 | Sprint Review | Team + Product | 60 min | Demo ¦ Velocity ¦ Retrospective ¦ Next Sprint ¦ Dependencies | Velocity chart, completion stats | Partial | 2024-01-26