## Escalation Rules
Rule ID | Rule Name | Trigger Condition | Escalation Level | Auto Actions | Notification Recipients | SLA (Hours) | Active | Last Triggered
ESC001 | Blocker Duration | Blocker unresolved > 3 days | L1 - PM | Create escalation ticket, notify PM, add to daily standup | PM, Tech Lead | 4 | Yes | 2024-01-28
ESC002 | Critical Path Delay | Critical path task delayed > 2 days | L2 - Director | Email Director, schedule war room, pause dependent tasks | PM, Director, Stakeholders | 2 | Yes | 2024-01-30
ESC003 | Budget Threshold | Project spend > 90% of budget with < 80% complete | L2 - Director + Finance | Alert Finance, freeze non-critical spend, executive summary | PM, Director, Finance, CFO | 1 | Yes | Never
ESC004 | Resource Overload | Team member utilization > 120% for > 1 week | L1 - PM | Alert PM, suggest reallocation, flag in resource dashboard | PM, HR | 24 | Yes | 2024-01-29
ESC005 | Milestone Slip | Milestone forecast > 5 days late | L2 - Director | Update stakeholders, trigger recovery planning, SteerCo alert | PM, Director, Stakeholders | 4 | Yes | 2024-01-30
ESC006 | Risk Score Threshold | Risk score >= 8 (High/Critical) | L2 - Director | Add to risk register, notify risk owner, schedule review | PM, Risk Owner, Director | 4 | Yes | 2024-01-25
ESC007 | Velocity Drop | Sprint velocity drops > 30% from average | L1 - PM | Root cause analysis request, team health check, PM alert | PM, Scrum Master | 8 | Yes | 2024-01-29
ESC008 | Dependency Failure | Predecessor task not completed by successor start date | L1 - PM | Block successor task, notify both task owners, PM alert | PM, Task Owners | 2 | Yes | 2024-01-30

## Notification Log
Notification ID | Timestamp | Type | Priority | Project | Subject | Recipients | Channel | Status | Acknowledged | Triggered By Rule
NOT001 | 2024-01-30 09:15 | Escalation | Critical | DPLAT | CRITICAL: Kafka blocker exceeds 6 days - CTO escalation | CTO, Nancy Drew, Maria Garcia | Email + Slack + SMS | Sent | Yes | ESC001
NOT002 | 2024-01-30 09:30 | Alert | High | DPLAT | Budget burn rate exceeds forecast by 15% | Nancy Drew, Finance | Email + Slack | Sent | Yes | ESC003
NOT003 | 2024-01-30 10:00 | Reminder | Medium | ECOM | Weekly status report due tomorrow | Rachel Green | Email | Scheduled | N/A | Manual
NOT004 | 2024-01-30 11:45 | Escalation | Critical | DPLAT | ETL credentials blocker - dependency failure | Nancy Drew, Chen Wei, IT Ops | Email + Slack | Sent | No | ESC008
NOT005 | 2024-01-30 14:00 | Status Update | Low | MOB | Mobile App v2.0 - Sprint 5 completed | Tom Harris, Stakeholders | Email | Sent | N/A | Auto-Status
NOT006 | 2024-01-29 16:30 | Alert | High | ECOM | Payment gateway sandbox still down | Rachel Green, Mike Johnson | Email + Slack | Sent | Yes | ESC001
NOT007 | 2024-01-29 17:00 | Escalation | Critical | DPLAT | Data engineer resignation - knowledge transfer critical | Nancy Drew, HR, CTO | Email + Slack + SMS | Sent | Yes | Manual
NOT008 | 2024-01-28 10:00 | Reminder | Medium | SOC2 | SOC2 audit prep checklist reminder | Compliance Lead, Security Team | Email | Sent | Yes | Manual
NOT009 | 2024-01-28 14:30 | Alert | High | DPLAT | Snowflake costs 40% over projection | Nancy Drew, Robert Kim, Finance | Email + Slack | Sent | Yes | ESC003
NOT010 | 2024-01-27 09:00 | Status Update | Low | ECOM | Sprint 4 velocity report available | Rachel Green, Team | Email | Sent | N/A | Auto-Status

## Action Recommendations
Recommendation ID | Project | Category | Recommendation | Impact | Effort | Confidence | Priority | Status | Owner
ACT001 | DPLAT | Resource | Hire Kafka contractor immediately - critical path blocked | Unblocks 21 story points, saves 10+ days | Low (procurement) | 95% | P0 - Immediate | Pending Approval | Nancy Drew
ACT002 | DPLAT | Technical | Implement batch processing fallback for streaming pipeline | Reduces streaming risk, enables partial delivery | Medium (3-5 days dev) | 85% | P1 - This Week | In Progress | Maria Garcia
ACT003 | ECOM | Risk Mitigation | Activate backup payment gateway (Adyen) for testing | Enables payment testing to continue | Low (configuration) | 90% | P1 - This Week | Approved | Mike Johnson
ACT004 | MOB | Scope | Defer accessibility features to v2.1 to meet launch date | Saves 8 story points, reduces risk | Low (backlog update) | 88% | P2 - This Sprint | Under Review | Tom Harris
ACT005 | DPLAT | Budget | Request 25% budget increase ($200K) or reduce scope | Enables project completion without cuts | Medium (approval process) | 75% | P0 - Immediate | Pending Approval | Nancy Drew
ACT006 | ECOM | Schedule | Fast-track API development with parallel workstreams | Saves 5 days on critical path | Medium (coordination) | 82% | P1 - This Week | Approved | Rachel Green
ACT007 | Portfolio | Communication | Schedule emergency SteerCo for DPLAT status | Aligns stakeholder expectations | Low (scheduling) | 100% | P0 - Immediate | Scheduled | PMO Director
ACT008 | SOC2 | Compliance | Accelerate evidence collection - audit moved up 2 weeks | Ensures audit readiness | High (team effort) | 92% | P1 - This Week | In Progress | Compliance Lead

## Decision Support
Decision ID | Decision Required | Option A | Option A Pros | Option A Cons | Option A Score | Option B | Option B Pros | Option B Cons | Option B Score | Option C | Option C Pros | Option C Cons | Option C Score | AI Recommendation | Confidence | Decision Deadline
DEC001 | DPLAT: Continue with current plan vs. Reduce scope vs. Extend timeline | Continue current plan | No scope reduction, full delivery | 90% chance of 21-day delay, $250K overrun | 35 | Reduce scope by 20% | On-time delivery possible, budget control | Missing key features, stakeholder impact | 65 | Extend timeline 3 weeks | Full scope, manageable overrun | Stakeholder reset needed, opportunity cost | 55 | Option B - Reduce scope | 78% | 2024-02-01
DEC002 | ECOM: Use primary payment gateway (delayed) vs. Switch to backup | Wait for primary gateway | Preferred vendor, better rates | 7+ day delay, blocks testing | 45 | Switch to backup gateway | Immediate unblock, testing continues | Higher transaction fees, migration later | 75 | Parallel integration both | Flexibility, risk mitigation | Double effort, complexity | 60 | Option B - Switch to backup | 85% | 2024-01-31
DEC003 | MOB: Include accessibility in v2.0 vs. Defer to v2.1 | Include in v2.0 | Full compliance, better UX | 8 extra story points, 4-day delay risk | 60 | Defer to v2.1 | On-time launch, reduced risk | Compliance gap until v2.1 | 70 | Partial implementation | Core compliance, reduced scope | Technical debt, partial solution | 55 | Option B - Defer to v2.1 | 72% | 2024-02-05